## Real Work
Notes
1. 藍色可輸入，橙色勿動
2. 每新增一項 task，可自行將 expected，STD & VAR 三項公式一併拉下來
3. 若資料超過 row 50，請告知彥鈞
Effort
Percentage Confidence of Inteval Best to Worst |  | 80%
Devisor |  | 2.5631
Total VAR |  | 305.1223
Total STD |  | 17.4677
Total Expected Effort (50%) |  | 409.6667
Percentage Condidente of Total Expected Effort |  | 75%
Total Expected Effort (75%) |  | 421.4485
Percentage Condidente of Total Expected Effort |  | 2% | 10% | 16% | 20% | 25% | 30% | 40% | 50% | 60% | 70% | 75% | 80% | 84% | 90% | 98%
Effort Estimate |  | 373.7923 | 387.2808 | 392.2957 | 394.9654 | 397.8848 | 400.5066 | 405.2413 | 409.6667 | 414.0921 | 418.8268 | 421.4485 | 424.3679 | 427.0376 | 432.0525 | 445.541
WBS
Deadline | Item | Item branch | Task | Best | Most Likely | Worst | Expected (50%) | STD | VAR | Person in Charge | Start Date | Compelete % | Actual
Total |  |  |  | 181.5 | 306.5 | 429.5
| Ideas | Survey | Existing project comparison | 2 | 5 | 5 | 4.5 | 1.1705 | 1.37
|  |  | Survey report | 1.5 | 3 | 4 | 2.9167 | 0.97538 | 0.95137
|  | Requirements Analysis | Extract requirements | 2 | 4 | 5.5 | 3.9167 | 1.3655 | 1.8647
|  |  | Set goals | 1.5 | 2.5 | 4 | 2.5833 | 0.97538 | 0.95137
|  |  | Define character | 2 | 3 | 4.5 | 3.0833 | 0.97538 | 0.95137
|  |  | Use cases | 4.5 | 7 | 8.5 | 6.8333 | 1.5606 | 2.4355
|  |  | Define system requirements | 3 | 4.5 | 7 | 4.6667 | 1.5606 | 2.4355
|  |  | Write requirement document | 3 | 5.5 | 7.5 | 5.4167 | 1.7557 | 3.0824
2022-10-25 |  |  | milestone
|  | Development of Project Plans | Introduction | 1 | 2.5 | 8 | 3.1667 | 2.7311 | 7.4587
|  |  | Lifecycle | 2.5 | 3.5 | 4.5 | 3.5 | 0.7803 | 0.60887
|  |  | Work breakdown structure | 3 | 4.5 | 6.5 | 4.5833 | 1.3655 | 1.8647
2022-10-04 |  |  | Schedule | 1.5 | 2.5 | 3.5 | 2.5 | 0.7803 | 0.60887
|  |  | Resource | 6 | 10.5 | 14 | 10.3333 | 3.1212 | 9.742
|  |  | required knowledge and skill | 4 | 6 | 8 | 6 | 1.5606 | 2.4355
|  |  | training plan | 2 | 4.5 | 6 | 4.3333 | 1.5606 | 2.4355
2022-10-11 |  |  | milestone
| Risk Management and Project Control | Risk | Risk Analysis | 6.5 | 12.5 | 16 | 12.0833 | 3.7064 | 13.7377
|  |  | risk identification | 2 | 4 | 5 | 3.8333 | 1.1705 | 1.37
|  |  | risk assessment | 3 | 5 | 7 | 5 | 1.5606 | 2.4355
|  |  | risk classification | 1.5 | 3.5 | 4 | 3.25 | 0.97538 | 0.95137
|  |  | Risk control | 9 | 14.5 | 18 | 14.1667 | 3.5114 | 12.3297
|  |  | risk mitigation | 2.5 | 4.5 | 6 | 4.4167 | 1.3655 | 1.8647
|  |  | risk planning | 4.5 | 5.5 | 7 | 5.5833 | 0.97538 | 0.95137
|  |  | risk monitoring | 2 | 4.5 | 5 | 4.1667 | 1.1705 | 1.37
|  | Project Monitoring and Control | Project supervision | 5.5 | 8.5 | 11 | 8.4167 | 2.1458 | 4.6046
|  |  | data collection | 4 | 6 | 7 | 5.8333 | 1.1705 | 1.37
|  |  | earned value management | 1.5 | 2.5 | 4 | 2.5833 | 0.97538 | 0.95137
|  |  | Project control | 3 | 7 | 9 | 6.6667 | 2.3409 | 5.4799
|  |  | formal control | 1.5 | 3.5 | 4.5 | 3.3333 | 1.1705 | 1.37
|  |  | informal control | 1.5 | 3.5 | 4.5 | 3.3333 | 1.1705 | 1.37
2022-10-11 |  |  | milestone
| Website Design | Architecture Design | System architecture selection | 2.5 | 4 | 5.5 | 4 | 1.1705 | 1.37
|  |  | Design methods and tools | 3 | 4.5 | 5.5 | 4.4167 | 0.97538 | 0.95137
|  |  | System segmentation | 16 | 24 | 32 | 24 | 6.2424 | 38.968
|  |  | server | 4 | 6 | 8 | 6 | 1.5606 | 2.4355
|  |  | client | 3.5 | 5 | 6.5 | 5 | 1.1705 | 1.37
|  |  | database | 3.5 | 5 | 6.5 | 5 | 1.1705 | 1.37
|  |  | connector | 3 | 4.5 | 6 | 4.5 | 1.1705 | 1.37
|  |  | packet | 2 | 3.5 | 5 | 3.5 | 1.1705 | 1.37
|  |  | Subsystem interaction mode | 6 | 10 | 13 | 9.8333 | 2.7311 | 7.4587
|  |  | object mode | 2 | 3.5 | 4.5 | 3.4167 | 0.97538 | 0.95137
|  |  | control mode | 2 | 3.5 | 4.5 | 3.4167 | 0.97538 | 0.95137
|  |  | flowchart | 2 | 3 | 4 | 3 | 0.7803 | 0.60887
|  |  | System interface design | 4 | 6 | 8 | 6 | 1.5606 | 2.4355
|  | Component Design | Component function | 4 | 6 | 9 | 6.1667 | 1.9508 | 3.8055
|  |  | Input and Output | 3.5 | 5.5 | 7.5 | 5.5 | 1.5606 | 2.4355
|  |  | Algorithm requirements | 4 | 6.5 | 9.5 | 6.5833 | 2.1458 | 4.6046
|  | User Interface Design | Screen image | 2 | 4.5 | 7 | 4.5 | 1.9508 | 3.8055
|  |  | Object and Actions | 4.5 | 7 | 9.5 | 7 | 1.9508 | 3.8055
|  |  | Data structure design | 3 | 5.5 | 7.5 | 5.4167 | 1.7557 | 3.0824
|  |  | Database design | 2.5 | 4.5 | 6.5 | 4.5 | 1.5606 | 2.4355
|  | Algorithm Design | Input and Output | 2 | 4 | 5.5 | 3.9167 | 1.3655 | 1.8647
|  |  | Flowchart | 1.5 | 3.5 | 5 | 3.4167 | 1.3655 | 1.8647
2022-11-08 |  |  | milestone
| Development and Implementation | Establishment of Development Process | Individual development process | 3.5 | 5.5 | 8 | 5.5833 | 1.7557 | 3.0824
|  |  | Collaborative development process | 3.5 | 5.5 | 8 | 5.5833 | 1.7557 | 3.0824
|  | Implementation | Server | 7 | 10 | 15 | 10.3333 | 3.1212 | 9.742
|  |  | Client | 6 | 9 | 14 | 9.3333 | 3.1212 | 9.742
|  |  | Database | 5.5 | 9 | 13.5 | 9.1667 | 3.1212 | 9.742
|  |  | Connector | 4 | 8.5 | 13 | 8.5 | 3.5114 | 12.3297
|  |  | Packet | 3 | 5 | 7.5 | 5.0833 | 1.7557 | 3.0824
|  | Website Erection | Rent a host | 3 | 5 | 7.5 | 5.0833 | 1.7557 | 3.0824
|  |  | Buy a website | 2 | 4.5 | 6.5 | 4.4167 | 1.7557 | 3.0824
|  |  | Material preparation and visual design | 2.5 | 3.5 | 4.5 | 3.5 | 0.7803 | 0.60887
|  |  | Erect | 2.5 | 4 | 6 | 4.0833 | 1.3655 | 1.8647
|  |  | Website analysis and indexing | 2 | 3.5 | 5.5 | 3.5833 | 1.3655 | 1.8647
2022-12-06 |  |  | milestone
| Website Testing and Maintenance | Testing | Write a test plan document | 5 | 8 | 11 | 8 | 2.3409 | 5.4799
|  |  | Software testing | 10 | 18 | 26 | 18 | 6.2424 | 38.968
|  |  | preparation | 5 | 8 | 11 | 8 | 2.3409 | 5.4799
|  |  | execution | 2 | 4.5 | 7 | 4.5 | 1.9508 | 3.8055
|  |  | evaluation and control | 3 | 5.5 | 8 | 5.5 | 1.9508 | 3.8055
|  | Maintenance | Write a maintenance plan document | 4 | 7 | 9 | 6.8333 | 1.9508 | 3.8055
|  |  | Execution | 2 | 4.5 | 7 | 4.5 | 1.9508 | 3.8055
2022-11-22 |  |  | milestone

## 彥鈞s practice
| Smal Task |  | best | most likely | worst | STD | expected (50%)
Task 1 1.6 3.0 0.233 0.054 |  | Task 1 | 1.6 | 2 | 3.0 |  | 2.1 |  | NORMINV 就是 NORM.INV (可能 . 是舊的 API)
Task 2 1.8 4.0 0.367 0.134 |  | Task 2 | 1.8 | 2.5 | 4.0 |  | 2.6333 |  | NORMSINV for standard
Task 3 2.0 4.2 0.367 0.134 |  | Task 3 | 2.0 | 3 | 4.2 |  | 3.0333
Task 4 0.8 1.6 0.133 (1) 0.018 (2) |  | Task 4 | 0.8 | 1.2 | 1.6 |  | 1.2
Task 5 3.8 5.2 0.233 0.054 |  | Task 5 | 3.8 | 4.5 | 5.2 |  | 4.5
Task 6 3.8 6.0 0.367 0.134 |  | Task 6 | 3.8 | 5 | 6.0 |  | 4.9667
Task 7 2.2 3.4 0.200 0.040 |  | Task 7 | 2.2 | 2.4 | 3.4 |  | 2.5333
Task 8 0.8 2.2 0.233 0.054 |  | Task 8 | 0.8 | 1.2 | 2.2 |  | 1.3
Task 9 1.6 3.0 0.233 0.054 |  | Task 9 | 1.6 | 2.5 | 3.0 |  | 2.4333
Task 10 1.6 6.0 0.733 0.538 |  | Task 10 | 1.6 | 4 | 6.0 |  | 3.9333
TOTAL 20.0 38.6 - 1.22 (3) |  | TOTAL | 20.0 | 28.3 | 38.6 | 3.1 | 28.6333
|  | expeted (75%) | 30.7243
| Large Task |  | best | most likely | worst | STD | expected (50%) | VAR
|  | Task 1 | 1.6 | 2 | 3.0 | 0.23333 | 2.1 | 0.054444
|  | Task 2 | 1.8 | 2.5 | 4.0 | 0.36667 | 2.6333 | 0.13444
|  | Task 3 | 2.0 | 3 | 4.2 | 0.36667 | 3.0333 | 0.13444
|  | Task 4 | 0.8 | 1.2 | 1.6 | 0.13333 | 1.2 | 0.017778
|  | Task 5 | 3.8 | 4.5 | 5.2 | 0.23333 | 4.5 | 0.054444
|  | Task 6 | 3.8 | 5 | 6.0 | 0.36667 | 4.9667 | 0.13444
|  | Task 7 | 2.2 | 2.4 | 3.4 | 0.2 | 2.5333 | 0.04
|  | Task 8 | 0.8 | 1.2 | 2.2 | 0.23333 | 1.3 | 0.054444
|  | Task 9 | 1.6 | 2.5 | 3.0 | 0.23333 | 2.4333 | 0.054444
|  | Task 10 | 1.6 | 4 | 6.0 | 0.73333 | 3.9333 | 0.53778
|  | TOTAL | 20.0 | 28.3 | 38.6 |  | 28.6333 | 1.2167
|  |  |  | STD | 1.103 | expeted (75%) | 29.3773
| Large Task，not 6 |  | best | most likely | worst | STD | expected (50%) | VAR
|  | Task 1 | 1.6 | 2 | 3.0 | 0.54621 | 2.1 | 0.29835
Percentage Confidence |  | Task 2 | 1.8 | 2.5 | 4.0 | 0.85833 | 2.6333 | 0.73674
80% |  | Task 3 | 2.0 | 3 | 4.2 | 0.85833 | 3.0333 | 0.73674
Devisor |  | Task 4 | 0.8 | 1.2 | 1.6 | 0.31212 | 1.2 | 0.09742
2.5631 |  | Task 5 | 3.8 | 4.5 | 5.2 | 0.54621 | 4.5 | 0.29835
|  | Task 6 | 3.8 | 5 | 6.0 | 0.85833 | 4.9667 | 0.73674
|  | Task 7 | 2.2 | 2.4 | 3.4 | 0.46818 | 2.5333 | 0.21919
|  | Task 8 | 0.8 | 1.2 | 2.2 | 0.54621 | 1.3 | 0.29835
|  | Task 9 | 1.6 | 2.5 | 3.0 | 0.54621 | 2.4333 | 0.29835
|  | Task 10 | 1.6 | 4 | 6.0 | 1.7167 | 3.9333 | 2.947
|  | TOTAL | 20.0 | 28.3 | 38.6 |  | 28.6333 | 6.6672
|  |  |  | STD | 2.5821 | expeted (75%) | 30.3749
[6 empty] | expeted (80%) | 30.8065
[6 empty] | expeted (90%) | 31.9424

## 彥鈞s backup
Percentage Confidence of Inteval Best to Worst |  |  | 80% |  | Total VAR | 6.6672 |  | Total Expected Effort (50%) |  | 28.6333
Devisor |  |  | 2.5631 |  | Total STD | 2.5821 |  | Percentage Condidente of Total Expected Effort |  | 75%
[8 empty] | Total Expected Effort (75%) |  | 30.3749
Item | Task | Best | Most Likely | Worst | Expected (50%) | STD | VAR | Person in Charge | Start Date | Compelete % | Actual
測試資料
| Task 1 | 1.6 | 2 | 3 | 2.1 | 0.54621 | 0.29835
| Task 2 | 1.8 | 2.5 | 4 | 2.6333 | 0.85833 | 0.73674
| Task 3 | 2 | 3 | 4.2 | 3.0333 | 0.85833 | 0.73674
| Task 4 | 0.8 | 1.2 | 1.6 | 1.2 | 0.31212 | 0.09742
| Task 5 | 3.8 | 4.5 | 5.2 | 4.5 | 0.54621 | 0.29835
| Task 6 | 3.8 | 5 | 6 | 4.9667 | 0.85833 | 0.73674
| Task 7 | 2.2 | 2.4 | 3.4 | 2.5333 | 0.46818 | 0.21919
| Task 8 | 0.8 | 1.2 | 2.2 | 1.3 | 0.54621 | 0.29835
| Task 9 | 1.6 | 2.5 | 3 | 2.4333 | 0.54621 | 0.29835
| Task 10 | 1.6 | 4 | 6 | 3.9333 | 1.7167 | 2.947